Mitsue Project — Implementation Plan

From Concept to Reality

April 2026

Overview

This plan breaks the implementation of the Mitsue Sustainable Energy & AI Data Center project into five phases over the first three years, with a clear path from concept to operational pilot. Each phase has defined deliverables, funding requirements, and risk checkpoints.

The 25-year vision remains, but the first 3 years are the make-or-break period. Get the foundations right and the rest becomes possible.

Phase Overview

| Phase | Timeframe | Focus | Estimated Budget |
| --- | --- | --- | --- |
| 0. Pre-Foundation | Months 1–3 | Local trust, founding team, basic structure | ¥0–500,000 (self-funded) |
| 1. Foundation | Months 4–9 | NPO incorporation, feasibility studies | ¥3–8 million |
| 2. Pilot Design | Months 10–18 | Detailed engineering, partnerships, permits | ¥15–30 million |
| 3. Pilot Build | Months 19–30 | Construction of small first stage | ¥80–200 million |
| 4. Operation & Scale | Months 31+ | Operations, monitoring, expansion | Variable |

These ranges are realistic for rural Japan but conservative — actual costs vary widely depending on biomass equipment, fiber availability, and building condition.

Phase 0 — Pre-Foundation (Months 1–3)

Goal: Establish local trust and a small founding team before any public announcements or formal structures.

Critical Actions

- Private conversations with village leadership — village mayor, key council members. Listen first, present second.

- Conversations with 自治会 (community association) leaders in Sugano and surrounding hamlets.

- Identify 3–5 founding team members including at least one well-respected Japanese co-founder with rural credibility.

- Quiet conversations with 2–3 sympathetic landowners to gauge interest in cedar harvesting partnerships.

- Draft preliminary charter in Japanese and English (simple, 1–2 pages).

What NOT to Do in Phase 0

- No public announcements

- No website or social media yet

- No press contact

- No detailed financial commitments

Deliverables

- Founding team agreed (verbal commitments)

- Mitsue village leadership informed and supportive (or neutral)

- Draft charter document

- List of potential landowner partners

Phase 1 — Foundation (Months 4–9)

Goal: Establish the legal entity and complete feasibility studies that will enable serious funding applications.

1A. NGO Setup — Choosing the Right Structure

There are three relevant non-profit structures in Japan, with different tradeoffs:

Option A: 一般社団法人 (Ippan Shadan Hojin) — General Incorporated Association

- Easier to set up — registration only, no government approval needed

- Faster — typically 1–2 months to incorporate

- More flexible governance

- Recommended for the project's first 1–2 years

Option B: NPO法人 (NPO Hojin / 特定非営利活動法人) — Specified Nonprofit Corporation

- Requires prefectural government authorization (認証) — 4-month review period

- More public credibility for grants and donations

- Stricter regulations — minimum 10 members, 3 directors, 1 auditor; mandatory public disclosures

- Best path for long-term legitimacy and government grants

- Recommendation: Convert to this in year 2–3 when ready

Option C: 認定NPO法人 (Nintei NPO Hojin) — Certified NPO

- Highest credibility tier — donors get tax deductions

- Available 5+ years after NPO法人 incorporation (or special early certification one-time)

- Strict requirements — public donation thresholds, financial transparency

- Long-term goal — apply once track record is established

1B. Recommended Path for the Mitsue Project

Start as 一般社団法人, plan transition to NPO法人 after 18–24 months.

1C. Setup Requirements (一般社団法人)

- Minimum 2 founding members (社員)

- Minimum 1 director (理事), but 3+ is strongly recommended

- Articles of incorporation (定款) — drafted in Japanese, notarized

- Registered office address — can be in Mitsue

- Registration with Legal Affairs Bureau (法務局)

- Estimated cost: ¥110,000 registration tax + ¥50,000 notary + ¥100,000–300,000 if using a 行政書士 (administrative scrivener)

- Setup time: 4–8 weeks

1D. Recommended Founding Board Composition

- Representative Director (代表理事): ideally a respected Japanese co-founder

- Director — Technology: Rob (or rotating role)

- Director — Forestry/Local: a local forestry expert or village elder

- Director — Finance/Operations: someone with NPO management experience

- Auditor (監事): an independent person, ideally with accounting knowledge

1E. Feasibility Studies to Commission

These are the single most important documents for unlocking serious funding. Get these right.

- Forestry Feasibility Study (~¥1.5–3M)

  - Biomass yield from candidate sugi plots

  - Transportation costs from steep terrain

  - Native forest restoration plan and timeline

  - Carbon sequestration estimate

  - Recommended providers: forestry consultants connected to 日本林業協会 or 林野庁

- Energy Systems Feasibility Study (~¥2–4M)

  - Biomass plant sizing options

  - Biogas potential

  - Grid connection and FIT/FIP eligibility

  - Battery storage requirements

  - Heat recovery opportunities

- Building & Site Assessment (~¥1–2M)

  - Structural condition of school building

  - Seismic compliance requirements

  - Required renovations for data center use

  - Zoning and permit considerations

- Connectivity Assessment (~¥0.3–0.5M)

  - Current fiber capacity to Mitsue

  - Upgrade requirements and costs

  - Coordination with NTT / regional providers

Phase 1 Deliverables

- Legal entity registered

- Feasibility studies completed

- Letter of interest from Mitsue village government

- Bilingual project website (basic, professional)

- Initial advisory board formalized

- Bank account, accounting system in place

Phase 2 — Pilot Design (Months 10–18)

Goal: Convert feasibility studies into detailed engineering plans, secure pilot funding, and finalize partnerships.

Key Activities

- Detailed engineering and architectural plans

- Permitting (forestry, building, METI biomass licensing, FIT registration)

- Partnership agreements with landowners (template contract)

- Vendor selection for biomass equipment, data center hardware, IT

- Major funding applications submitted

- Hiring of first 2–3 part-time staff

Funding Targets — Phase 2

- Aiming for ¥30–50M secured by end of Phase 2 to cover Phase 2 costs and Phase 3 startup

Phase 3 — Pilot Build (Months 19–30)

Goal: Build a small but real version of the project — a functioning proof of concept.

Suggested Pilot Scope

- Forestry: First 5–10 hectares of sugi harvested and replanted

- Energy: Small biomass boiler + heat recovery (start with thermal, not electrical generation; cheaper and more efficient)

- Building: Renovate one wing of the school for office and small server room

- Data center: ~10–20 servers, edge computing focus

- EV charging: 2–4 charging stations as visible village benefit

Why Start Small

- Demonstrates feasibility before larger spending

- Builds operational know-how

- Creates fundable success story for Phase 4 expansion

- Lowers risk if a major component proves harder than expected

Phase 4 — Operation & Scale (Months 31+)

This is when the project transitions from "construction" to "ongoing institution." Topics for this phase include scaling forestry operations, expanding the data center, replicating in other villages, and refining the financial model. Detailed planning for this phase happens in Year 2 once Phase 1 results are in.

Funding Strategy

Layered Funding Approach

The project should pursue multiple funding streams in parallel, never depending on a single source.

Layer 1 — Founding Capital (Phase 0–1)

- Self-funded / founder contributions: ¥0.5–2M

- Friends-and-family / advisor support: ¥1–3M

- Small private donations: ¥1–3M

Layer 2 — Government Grants (Phase 1–2)

Most relevant programs:

- 地方創生関係交付金 (Regional Revitalization Grants) — Cabinet Office; for projects creating jobs and stemming rural depopulation. Typically ¥5–50M per project.

- 林野庁 / Forestry Agency subsidies — for native forest restoration, sugi conversion, forest road infrastructure

- NEDO grants — New Energy and Industrial Technology Development Organization; renewable energy R&D

- METI green technology subsidies — for biomass and innovative energy projects

- Nara Prefecture rural development grants — varies by year; check 奈良県地域創造課

- Mitsue village local subsidies — small but politically meaningful

Recommendation: Hire a 行政書士 (administrative scrivener) experienced in grant applications. Cost: ¥200,000–500,000 per application. Worth every yen — Japanese government grant applications are notoriously demanding.

Layer 3 — Foundation & Philanthropy

- The Nippon Foundation (日本財団) — Asia's leading grantmaker for social challenges

- Japan Fund for Global Environment (地球環境基金) — environmental conservation grants

- Japan Foundation Global Partnerships grants — rural revitalization, AI, green tech

- Toyota Foundation — community and rural projects

- International foundations: MacArthur, Rockefeller (less likely but possible given Joi Ito network)

Layer 4 — Corporate Partnerships

- Dutch corporates in Japan: Philips, ASML, Heineken, Royal HaskoningDHV (water expertise), Arcadis

- Japanese tech corporates: SoftBank, NTT (data center / connectivity), Hitachi

- Forestry-related: Sumitomo Forestry, Mitsui Bussan

- Approach: Position as CSR / sustainability investment, not pure donation

Layer 5 — Revenue (Phase 3+)

- Data center hosting fees

- Electricity sales (if FIT-registered)

- Heat sales to greenhouses or community

- EV charging fees

- Carbon credits (J-Credit certification)

- Forestry products beyond biomass (timber, lumber)

- Educational tourism / consulting (sharing the playbook)

Realistic Funding Scenario for First 3 Years

| Source | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- |
| Founder/private | ¥3M | ¥2M | ¥1M |
| Government grants | ¥5M | ¥30M | ¥80M |
| Foundations | ¥3M | ¥10M | ¥20M |
| Corporate partnerships | ¥0 | ¥5M | ¥30M |
| Revenue | ¥0 | ¥0 | ¥3M |
| Total | ¥11M | ¥47M | ¥134M |

These are illustrative targets, not commitments. Real numbers will depend heavily on which grants are won.

Legal & Regulatory Checklist

Entity & Tax

- 一般社団法人 incorporation

- Tax registration (法人税, 消費税)

- Bank account opening

- Accounting system (consider 弥生会計 or equivalent)

- Annual financial reporting

Project-Specific Permits

- Forestry permits — 伐採届出 (cutting notification) under Forest Act

- Land use changes — coordination with 農業委員会 if any agricultural land involved

- Building conversion permits — Building Standards Act (建築基準法)

- Fire and safety — biomass plant requires 消防 approvals

- Electrical equipment — 電気事業法 compliance for power generation

- FIT/FIP registration — METI process for grid feed-in

- Environmental impact — depending on scale, may require 環境アセスメント

- Data center compliance — APPI (privacy), cybersecurity standards

Recommended Professional Support

- 行政書士 (administrative scrivener) — for permits, NPO setup, grant applications. Local Nara-based ideal.

- 公認会計士 / 税理士 (accountant / tax advisor) — for financial setup and reporting

- 弁護士 (lawyer) — for landowner contracts, partnership agreements (consult, don't retain full-time yet)

- Patent attorney — only if novel technology IP needs protection

Risk Management

Top Risks and Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Local community resistance | Medium | High | Phase 0 trust-building before any announcements |
| Forestry economics worse than expected | High | High | Independent feasibility study early; have alternative biomass sources ready |
| Funding gaps between phases | Medium | High | Diversified funding, never depend on one source; phase budgets conservatively |
| Founder dependency on Rob | Medium | High | Strong co-founders, documented processes, succession plan |
| Building unsuitable for data center | Low | High | Early structural assessment in Phase 1 |
| Fiber connectivity insufficient | Medium | Medium | Early NTT consultation; consider satellite/microwave backup |
| Regulatory delays | High | Medium | Start permits early; build buffer into timeline |
| Team conflict / mission drift | Medium | High | Clear charter, regular reviews, term limits |

Immediate Next Steps (Next 30 Days)

- Identify and approach the Japanese co-founder — most important single decision

- Schedule informal meeting with Mitsue village mayor

- Reach out to 1–2 candidate 行政書士 in Nara for initial consultations

- Draft a 2-page charter in Japanese and English

- Confirm advisory commitments from Joi Ito and Ray Ozzie in writing (even informal)

- Confirm support letter intent from Sandra Pellegrom / Dutch Consulate

- Open a project Slack/Signal/email list for the founding team

Recommended Reading & Resources

- Japan NPO Center (jnpoc.ne.jp) — primary resource for NPO setup

- 林野庁 (Forestry Agency) website — forestry subsidies and regulations

- NEDO — renewable energy grant programs

- The Nippon Foundation — major funder for social initiatives

- METI — biomass and FIT/FIP regulations

- Cabinet Office Regional Revitalization portal (chisou.go.jp)

Closing Note

This plan is intentionally conservative in pace and ambitious in vision. The biggest mistake similar projects make is moving too fast publicly before securing local social license, then collapsing under the weight of expectations they cannot meet.

The Mitsue Project's strength is its 25-year horizon. There is no rush in year one — there is a long, careful build of trust, structure, and capability that will determine whether year 25 looks like success or failure.

Slow is smooth. Smooth is fast.

Rob Oudendijk — YR-Design / Safecast

Mitsue, Nara Prefecture, Japan

April 2026