## Master To-Do
Mitsue Project — Master To-Do List
Status options: Not started • In progress • Blocked • Done
Phase | Task | Owner | Status | Due | Priority | Notes
Phase 0 | Private meeting with Mitsue village mayor | Rob + JP co-founder | Not started |  | High | Listen first, present second
| Meet 自治会 leaders in Sugano + surrounding hamlets | JP co-founder | Not started |  | High
| Identify and confirm Japanese co-founder | Rob | In progress |  | Critical | Most important single decision
| Identify 3–5 founding team members | Rob | Not started |  | High | Verbal commitments OK
| Quiet conversations with 2–3 sympathetic landowners | JP co-founder | Not started |  | Medium | Gauge sugi harvesting interest
| Draft 2-page preliminary charter (JP + EN) | Rob | Not started |  | High
| Confirm advisory commitments (Ray Ozzie) in writing | Rob | Done |  | High | 2026-05-05 confirmed in Slack private channel.
| Diplomatic support outreach — not pursued | Rob | Rejected |  | High | Dutch consulate support not pursued.
| Reach out to 1–2 candidate 行政書士 in Nara | Rob | Not started |  | Medium | For permits + grant apps
| Open project Slack/Signal/email list | Rob | Not started |  | Low
Phase 1 | Draft 定款 (articles of incorporation) | 行政書士 | Not started |  | High
| Notarize 定款 | 行政書士 | Not started |  | High | ~¥50,000
| Register 一般社団法人 with Legal Affairs Bureau | 行政書士 | Not started |  | Critical | ~¥110,000 registration tax
| Tax registration (法人税, 消費税) | 税理士 | Not started |  | High
| Open corporate bank account | Representative Director | Not started |  | High
| Set up accounting system (e.g. 弥生会計) | 税理士 | Not started |  | Medium
| Commission Forestry Feasibility Study | Tech Director | Not started |  | Critical | ¥1.5–3M, 林野庁-aligned consultant
| Commission Energy Systems Feasibility Study | Tech Director | Not started |  | Critical | ¥2–4M
| Commission Building & Site Assessment | Tech Director | Not started |  | Critical | ¥1–2M, school structural check
| Commission Connectivity Assessment | Tech Director | Not started |  | High | ¥0.3–0.5M, NTT coordination
| Secure letter of interest from Mitsue village government | Representative Director | Not started |  | High
| Launch bilingual project website (basic, professional) | Rob | Not started |  | Medium
| Formalize advisory board | Rob | Not started |  | Medium
Phase 2 | Detailed engineering & architectural plans | Tech Director + vendor | Not started |  | Critical
| File 伐採届出 (cutting notification) | 行政書士 | Not started |  | High | Forest Act
| Building conversion permits (建築基準法) | 行政書士 | Not started |  | High
| 消防 approvals for biomass plant | 行政書士 | Not started |  | High
| 電気事業法 compliance for power generation | 行政書士 | Not started |  | High
| FIT/FIP registration with METI | 行政書士 | Not started |  | High
| Landowner partnership template contract | 弁護士 | Not started |  | High
| Vendor selection — biomass equipment | Tech Director | Not started |  | High
| Vendor selection — data center hardware | Tech Director | Not started |  | High
| Submit 地方創生 grant application | 行政書士 + Rep Dir | Not started |  | Critical | Cabinet Office
| Submit 林野庁 forestry subsidy application | 行政書士 | Not started |  | Critical
| Submit NEDO grant application | 行政書士 | Not started |  | High
| Submit METI green tech subsidy application | 行政書士 | Not started |  | High
| Submit Nippon Foundation grant application | Rob | Not started |  | High
| Submit Japan Fund for Global Environment application | Rob | Not started |  | High
| Initial outreach — Dutch corporates (Philips, ASML, RHDHV, Arcadis) | Rob | Not started |  | Medium | CSR / sustainability framing
| Initial outreach — JP corporates (NTT, SoftBank, Sumitomo Forestry) | JP co-founder | Not started |  | Medium
| Hire first 2–3 part-time staff | Operations Director | Not started |  | Medium
Phase 3 | Harvest first 5–10 ha of sugi | Forestry Director | Not started |  | Critical
| Replant native species on harvested plots | Forestry Director | Not started |  | Critical
| Install small biomass boiler + heat recovery | Tech Director + vendor | Not started |  | Critical | Thermal first, not electrical
| Renovate one wing of school for office + small server room | Tech Director | Not started |  | Critical
| Install ~10–20 servers (edge compute) | Tech Director | Not started |  | High
| Install 2–4 EV charging stations | Tech Director | Not started |  | Medium | Visible village benefit
| Apply for J-Credit certification | Forestry Director | Not started |  | Medium | Carbon credits
Phase 4 | Begin convert to NPO法人 (18–24 months in) | Representative Director | Not started |  | High | Long-term legitimacy
| Establish ongoing operations team | Operations Director | Not started |  | High
| Publish open data + open methodology | Rob | Not started |  | Medium | Funder commitment
| Plan replication in 1–2 other villages | Rep Dir + Rob | Not started |  | Medium
Cross-cutting | Diversify funding — never depend on one source | Rob | Ongoing |  | Critical | Risk mitigation
| Document succession plan (reduce Rob-dependency) | Rep Dir | Not started |  | High
| Quarterly board reviews | Rep Dir | Ongoing |  | Medium
| Annual financial reporting | 税理士 | Ongoing |  | High

## Legal Checklist
Legal & Regulatory Checklist
Category | Item | Done? | Notes
Entity & Tax | 一般社団法人 incorporation | ☐
Entity & Tax | Tax registration (法人税, 消費税) | ☐
Entity & Tax | Bank account opening | ☐
Entity & Tax | Accounting system (e.g. 弥生会計) | ☐
Entity & Tax | Annual financial reporting | ☐
Permits | Forestry permit — 伐採届出 (Forest Act) | ☐
Permits | Land use coordination — 農業委員会 if agricultural land | ☐
Permits | Building conversion — 建築基準法 | ☐
Permits | Fire & safety — 消防 approvals for biomass | ☐
Permits | Electrical — 電気事業法 compliance | ☐
Permits | FIT/FIP registration — METI | ☐
Permits | Environmental impact — 環境アセスメント (if scale triggers) | ☐
Permits | Data center compliance — APPI + cybersecurity | ☐
Pro support | Engage 行政書士 (Nara-based ideal) | ☐
Pro support | Engage 公認会計士 / 税理士 | ☐
Pro support | 弁護士 consult — landowner contracts | ☐
Pro support | Patent attorney — only if novel IP arises | ☐

## Risk Register
Risk Register
Risk | Likelihood | Impact | Mitigation | Owner
Local community resistance | Medium | High | Phase 0 trust-building before any announcements | Rep Dir
Forestry economics worse than expected | High | High | Independent feasibility study early; alt. biomass sources ready | Forestry Dir
Funding gaps between phases | Medium | High | Diversified funding; never depend on one source; conservative phase budgets | Rob
Founder dependency on Rob | Medium | High | Strong co-founders, documented processes, succession plan | Rep Dir
Building unsuitable for data center | Low | High | Early structural assessment in Phase 1 | Tech Dir
Fiber connectivity insufficient | Medium | Medium | Early NTT consultation; satellite/microwave backup | Tech Dir
Regulatory delays | High | Medium | Start permits early; build buffer into timeline | 行政書士
Team conflict / mission drift | Medium | High | Clear charter, regular reviews, term limits | Rep Dir